| Calendar of Performance Management Tasks | 2010 | 2011 | 2012 |
| --- | --- | --- | --- |
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 |
| 1. Vet draft PMP with key Stakeholders and achieve staff consensus on final |  |  |  |  |  |  |  |  |  |  |  |  |
| 2. Submit PMP to USAID – Renegotiate Quarterly Report Format |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. Negotiate with USAID on “F” indicators to be incorporated |  |  |  |  |  |  |  |  |  |  |  |  |
| 4. Train staff in data collection methods and reporting responsibilities |  |  |  |  |  |  |  |  |  |  |  |  |
| 5. Design and train staff in Excel trend graph generation – common drive |  |  |  |  |  |  |  |  |  |  |  |  |
| 6. Establish all baselines and enter in Excel common drive |  |  |  |  |  |  |  |  |  |  |  |  |
| 7. Do a data quality assessment on baseline data |  |  |  |  |  |  |  |  |  |  |  |  |
| 8. Collect data for Quarterly Reports |  |  |  |  |  |  |  |  |  |  |  |  |
| 9. Submit Quarterly Reports |  |  |  |  |  |  |  |  |  |  |  |  |
| 10. Review data with key Stakeholders for feedback |  |  |  |  |  |  |  |  |  |  |  |  |
| 11. Provide data plus additional information for USAID Portfolio Review |  |  |  |  |  |  |  |  |  |  |  |  |
| 12. Survey Municipalities: fugitive data |  |  |  |  |  |  |  |  |  |  |  |  |
| 12. Review/revise PMP |  |  |  |  |  |  |  |  |  |  |  |  |
| 13. Conduct midterm evaluation |  |  |  |  |  |  |  |  |  |  |  |  |
| 14. Conduct final evaluation |  |  |  |  |  |  |  |  |  |  |  |  |